## Master Activity
Activity | In Original Scope | Issue/ Blocker | Impact to Feb 15 | Resolver | When | Comment

## Summary
Count of Application | Column Labels
Dups | 2017-02-15 | TBD | (blank) | Grand Total
Yes
Client360 | 1 |  |  | 1
Cystal+ | 3 |  | 3 | 6
EDL | 1 |  |  | 1
No
Client360 | 7 |  |  | 7
Cystal+ | 6 | 11 | 16 | 33
EDL | 12 | 1 |  | 13
GTS | 1 |  |  | 1
(blank)
Open Data | 1 |  |  | 1
Grand Total | 32 | 12 | 19 | 63

## Data Ingestion
Priority | Original Source | Application | DBNAME | Domain Name | Dup? | Comment | Internal/ External | IMAP # | Data Set | Asset Owner | Ingestion Lead | Business Meta Data Loaded | Techincal Meta Data Validated | Access Requirememnts Defined | Access Requirements Physically Implemented | Bluegroup Created | Bluegroup linked to physical design | DOU | Functional ID Created | Refresh Schedule | Planned Ingestion Date | Ingestion Validated | Contains PI/SPI | Data Acqusition Review Date | Data Acqusition Review Status | Data Ingestion Review Date | Data Ingestion Review Status | Data Quality Review Date | Data Quality Review Status | Metadata Mgt Review Date | Metadata Mgt Review Status | Data Access & Security Review Date | Data Access & Security Review Status
TBD | EDL | OIM |  |  |  | No data, just metadata | Internal
2017-02-15 | EDL | MAPICS | A07PROD | Supply Chain |  |  | Internal | MBHT-S003694 |  | Sergio Daniel Garcia Ruiz
2017-02-15 | EDL | S&SC Only (need app name) | BACC_DEV_ISCDLPOC_ISCDL | Supply Chain |  | ISCIW | Internal | LAN-000016 |  | XIN ZHAO
2017-02-15 | EDL | DSNP | DSNP | Supply Chain |  | SMS | Internal | PDON-L000094 |  | RAQUEL CRISTINA MORI DOS SANTOS
2017-02-15 | EDL | QRYPROD |  |  |  |  | Internal
2017-02-15 | EDL | OMCS | ODRPTDB | Supply Chain |  |  | Internal | MUT-000002 |  | LiHua Qu
2017-02-15 | EDL | SOAR | SOARDB1 | Supply Chain |  |  | Internal | GRA-000026 |  | Jason S. Lee
2017-02-15 | EDL | SAP ODS | R0ADB2 | Supply Chain |  | SAPP&R | Internal | TKUY-S000369 |  | Myrna Lizeth Veloquio Moreno
2017-02-15 | EDL | Client Data EDL Respository | BACC_DEV_CLD_DATALAKE | Client Information |  | Put in 0.5, rationalize in 1.0 | Internal | No DOU |  | Sunita Menon
2017-02-15 | EDL | BP Data Mart | EUBADB2A | Client Information |  | BPDM | Internal | P_L-000003 |  | XIN XIN YANG
2017-02-15 | EDL | CISF |  |  |  |  | Internal
2017-02-15 | EDL | CGSP | ISMTODS | Client Information | Y | really ISMT ODS | Internal | GTH-000003 | CGSP Schemas | Cara Moore
2017-02-15 | EDL | SalesConnect | SCIWSTG | Client Information |  | ESA | Internal | SBEN-L000019 |  | Annette G. Irby
2017-02-15 | EDL | SDFDM | SDFDM | Client Information |  |  | Internal | SCA-000003 |  | MELISA AVILA VAZQUEZ
2017-02-15 | Cystal+ | MPW | BACC_PRD_IDM_IIW | Marketing |  | includes MDB | Internal | FRA-000032 |  | Stella C. Gabor
2017-02-15 | Cystal+ | BMSIW | ? |  |  | aka SIW? | Internal | JKUI-S000005 |  | ANGELICA HERNANDEZ MARTINEZ
2017-02-15 | Cystal+ | LDW | ? |  |  |  | Internal | BAR-000001 |  | Annette McGowan
2017-02-15 | Cystal+ | CAPIQ | CAPIQ | Financial Management |  | Usage issues | External |  |  | Daniel Benoit
| Cystal+ | TOP | ? |  | Y | not used | Internal | GTH-000003 | TOP Schemas | Cara Moore
TBD | Cystal+ | Google News |  |  |  |  | External
TBD | Cystal+ | Bing |  |  |  |  | External
TBD | Cystal+ | Blekko |  |  |  | not used | External
TBD | Cystal+ | Geomap |  |  |  | open source API | External
2017-02-15 | Cystal+ | GBT |  |  |  | should pull XML from TMT. No DOU needed | Internal | NOIMAP
| Cystal+ | Industry Blueprint Solutions |  |  |  |  | Internal
| Cystal+ | Techline |  |  |  |  | Internal
| Cystal+ | MTM Product Descriptions |  |  |  | MIW (Manufacturing Information Warehouse) | Internal | MHAN-L000005 |  | Timothy P. Barritt
| Cystal+ | TSS MVS Offerings |  |  | Y | MIW (Manufacturing Information Warehouse) | Internal
| Cystal+ | TSS Product Offerings |  |  | Y | MIW (Manufacturing Information Warehouse) | Internal
TBD | Cystal+ | Harte Hanks (CTIOB) |  |  |  | MPW | External
| Cystal+ | FMS |  |  |  | s/b FMS CMDW | Internal | FBC-000019 |  | MELISA AVILA VAZQUEZ
| Cystal+ | PEP |  |  |  | Notes DB | Internal
2017-02-15 | Cystal+ | HG Data |  |  | Y | MPW | External
2017-02-15 | Cystal+ | iProfile |  |  | Y | MPW | External
| Cystal+ | Bluepages |  |  |  |  | Internal
TBD | Cystal+ | Wikipedia |  |  |  | public API | External
TBD | Cystal+ | Twitter |  |  |  |  | External
TBD | Cystal+ | RSS Feeds |  |  |  | Need detail list of sites | External
| Cystal+ | BDW |  |  |  |  | Internal | LNI-000002 |  | YUE CHEN
| Cystal+ | Emptoris |  |  |  |  | Internal
| Cystal+ | SQEMS |  |  |  |  | Internal
| Cystal+ | DPL |  |  |  | Denied Party List Notes DB | Internal
| Cystal+ | Ombudsman |  |  |  | Notes DB | Internal | GRA-000020 |  | Jeffrey W. Gray
| Cystal+ | BCP |  |  |  | Business Continuity Program Notes DB | Internal
| Cystal+ | SCT |  |  |  | Supplier Communication Tool | Internal
| Cystal+ | SPE |  |  |  | Supplier Performance Evaluation, done in Emptoris now. Part of BDW pull | Internal | Sunset
| Cystal+ | TIP Deals |  |  |  |  | Internal
TBD | Cystal+ | Patents |  |  |  | Orbit custom API | External
2017-02-15 | Cystal+ | RDc |  |  | Y | either MPW or LDW | Internal | MPW
2017-02-15 | Cystal+ | DNB |  |  |  | MPW | External | MPW
| Cystal+ | BAIW |  |  |  |  | Internal
TBD | Cystal+ | Reuters |  |  |  | Public API | External
TBD | Cystal+ | Yahoo Finance |  |  |  | Public API | External
2017-02-15 | Client360 | Medallia |  |  | Y | Sourced from MPW | Internal | MPW |  |  | Archan
2017-02-15 | Client360 | IDM | BACC_PRD_IDM_ACS | Client Information |  |  | Internal | FRA-000031 |  | Donato A. Longo | Archan
2017-02-15 | Client360 | RDC | RDC | Client Information |  |  | Internal | TRD-000020 |  | Luiz Henrique Ejzemberg | Archan
2017-02-15 | Client360 | ISMT | ISMTODS | Client Information |  | really ISMT ODS | Internal | GTH-000003 |  | Cara Moore | Archan
2017-02-15 | Client360 | Softlayer | ? |  |  |  | External |  |  | contact is Steve Gardner | Archan
2017-02-15 | Client360 | DSW | ? |  |  |  | Internal | RVEH-S000162 |  | Jiening Lai | Archan
2017-02-15 | Client360 | CI PDA ??? | BACC_PRD_EAPDA_EAPDA | Client Information |  | part of RDC EAL Record | Internal | TRD-000020 |  | Luiz Henrique Ejzemberg | Archan
2017-02-15 | Client360 | SASSBL |  |  |  | sub system of DSW | Internal |  |  |  | Archan
2017-02-15 | GTS | SRM
2017-02-15 | Open Data | Test | OPENDATA.PLANTS | Testing |  | Open data set (see https://catalog.data.gov/dataset/plants) | External |  |  | USDA, NRCS. 2017. The PLANTS Database (http://plants.usda.gov, 9 February 2017). National Plant Data Team, Greensboro, NC 27401-4901 USA. | Daniel Bauer | [9 empty] | 2017-02-09 | 2017-02-09

## Table List
Lake Source | Data Source | Table Name | Date Completed | Min Date Value | Max Date Value | Last Update | Test Status | Update Schedule | Validated by | Date Validated | Tester Comment | Directory location | Developer Comment
C+ | MPW | mpw_iiw_b2bmsi2.v_bms_ctrct | 2017-01-29 | dq | dq | 2016-12-22 | Pass | [5 empty] | dq = data quality issue (here and onwards)
C+ | MPW | mpw_iiw_b2bmsi2.v_bms_offerg_cmpnt_ref | 2017-01-29 |  |  | 2016-01-04 | Pass
C+ | MPW | mpw_iiw_b2bmsi2.v_bms_offerg_ref | 2017-01-29 |  |  | 2017-01-18 | Pass
C+ | MPW | mpw_iiw_b2bmsi2.v_bms_wrk_ord_num | 2017-01-29 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2FNCE2.v_revn_cy | 2017-01-29 | 2016-04-19 | 2016-12-13 | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2FNCE2.v_revn_pys | 2017-01-29 | 2014-08-15 | 2016-01-21 | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INAT2.v_comp_rdc_client1_xref | 2017-01-29 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INAT2.v_indiv_on_page | 2017-01-29 |  |  | 2017-01-25 | Pass
C+ | MPW | MPW_IIW_V2INAT2.v_rdc_client | 2017-01-29 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INTR2.v_intrctn | 2017-01-29 | 2011-01-03 | 2024-07-27 | 2017-01-25 | Pass
C+ | MPW | MPW_IIW_V2OPTY2.v_opty_dtl | 2017-01-29 | 1996-03-18 | 2016-12-20 | 2016-12-20 | Pass
C+ | MPW | MPW_IIW_V2OPTY2.v_opty_role | 2017-01-29 |  |  | 2016-12-21 | Pass
C+ | MPW | MPW_IIW_V2OPTY2.v_opty_sc_prgrss | 2017-01-29 |  |  | 2016-12-20 | Pass
C+ | MPW | MPW_IIW_V2REFR2.v_ref_brand_rollup | 2017-01-29 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INAT2.duns_wb_actv | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INAT2.v_client_on_page | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INAT2.v_comp_duns_xref | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INAT2.v_duns_wb_actv_variations | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INAT2.v_rdc_cmr | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INAT2.v_rdc_site | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_ACS_ACS_BMNE2.v_hgdata_current | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_ACS_ACS_BMNE2.v_hgdata_norm_ww | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_ACS_ACS_CINS2.v_citdb_productinstall_2016_3m | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_ACS_ACS_CINS2.v_citdb_sitedescription_2016_3m | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_ACS_ACS_CINS2.v_competitive_ww_sum | 2017-01-18 | 2001-09-12 | 2018-01-01 | 2017-01-18 | Pass
C+ | MPW | MPW_ACS_ACS_CINS2.v_comp_hgdata_ww | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_ACS_ACS_CWAL2.v_dom_ultimate_bu_ww | 2017-02-02 | -- | -- | 2017-01-18 | Fail - Table does not exist
C+ | MPW | MPW_ACS_ACS_CWAL2.v_gbl_ultimate_bu_ww | 2017-02-02 | -- | -- | 2017-01-18 | Fail - Table does not exist
C+ | MPW | MPW_ACS_ACS_CWAL2.v_ntl_company_bu_ww | 2017-02-02 | -- | -- | 2017-01-18 | Fail - Table does not exist
C+ | MPW | MPW_ACS_ACS_CWAL2.v_xref_cust_duns_ww | 2017-02-02 | -- | -- | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INAT2.DUNS_WB_ACTV | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | MPW | MPW_IIW_V2INAT2.V_DUNS_WB_ACTV_VARIATIONS | 2017-01-18 |  |  | 2017-01-18 | Pass
C+ | RDC | RDC_CUST.sap_coverage_customer | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | RDC | RDC_CUST.sap_customer | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | RDC | RDC_CUST.sap_dim_sic_code | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | RDC | RDC_SAPR3.buying_group | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | RDC | RDC_SAPR3.global_buying_group | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | RDC | RDC_SAPR3.kna1 | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | RDC | RDC_SAPR3.legal_dom_client | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | RDC | RDC_SAPR3.legal_gbl_client | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.chsw_ww_cont_i | 2017-02-02 | dq | dq | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.chsw_ww_cont_partner | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.chsw_ww_ibase_inventory | 2017-02-02 | dq | dq | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.dsw_codes | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.dsw_customer | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.dsw_product | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.dsw_sales_ord_head | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.dsw_sales_ord_item | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.im_bluepage_ref | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.im_leg_ctry_ref | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.im_profit_center_ref | 2017-02-02 | 2008-12-18 | dq | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.lds_am_inventory | 2017-02-02 | dq | dq | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.lds_em_inventory | 2017-02-02 | dq | dq | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.mdm_ww_m_product_ref | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.rc_em_rev_groups | 2017-02-02 |  |  | 2017-01-17 | Pass
C+ | LDW | LDW_WSDIW.sw01_em_a_t02rsc | 2017-02-02 | dq | 2017-12-31 | 2017-01-17 | Pass
C+ | BMSIW | BMSIW_BMSIW.T510AMT_V | 2017-02-06 | 1992-09-29 | 2017-02-06 | 2017-02-06 | Pass | Monthly
C+ | BMSIW | BMSIW_BMSIW.T510BUS_V | 2017-02-06 | 2004-10-09 | 2017-02-03 | 2017-02-06 | Pass | Monthly
C+ | BMSIW | BMSIW_BMSIW.T510CHN_V | 2017-02-06 | 2007-08-01 | 2015-08-21 | 2017-02-06 | Pass | Monthly
C+ | BMSIW | BMSIW_BMSIW.T510CON_V | 2017-02-06 | 1991-05-23 | 2017-02-06 | 2017-02-06 | Fail - Cannot Select | Monthly
C+ | BMSIW | BMSIW_BMSIW.T510CTRY_V | 2017-02-06 | -- | -- | 2017-02-06 | Pass | Monthly
C+ | BMSIW | BMSIW_BMSIW.T510OFF_V | 2017-02-06 | 2014-10-18 | 2017-02-03 | 2017-02-06 | Pass | Monthly
C+ | BMSIW | BMSIW_BMSIW.T510STC_V | 2017-02-06 | 1995-03-30 | 2014-09-06 | 2017-02-06 | Pass | Monthly
C+ | BMSIW | BMSIW_BMSIW.T510SVT_V | 2017-02-06 | 1995-02-22 | 2014-09-06 | 2017-02-06 | Pass | Monthly
C+ | BMSIW | BMSIW_BMSIW.CFT_GEO_CTRY_V | 2017-02-06 | 2009-12-05 | 2014-12-09 | 2017-02-06 | Pass | Monthly
C+ | BMSIW | BMSIW_BMSIW.CURR_CRNCY_EXCH_V | 2017-02-06 | -- | -- | 2017-02-06 | Pass | Monthly
C+ | BMSIW | BMSIW_BMSIW.T510WRK_V | 2017-02-07 | 1990-09-25 | 2017-02-07 | 2017-02-07 | Fail - Cannot Select | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqBusinessDescription | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqBusinessDescriptionLong | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqKeyDev | 2017-02-05 | 2001-01-01 | 2017-02-03 | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqCompany | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqCompanyIndustryTree | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqCompanyStatusType | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqCompanyType | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqCountryGeo | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqCurrency | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqDataItem | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqExchange | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqExchangeRate | 2017-02-05 | 1900-01-01 | 2017-02-03 | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqFinancialData | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqFinUnitType | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqKeyDevToObjectToEventType | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqLatestInstanceFinPeriod | 2017-02-05 | 1976-05-30 | 2017-02-03 | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqPeriodType | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqPrivateFinPeriod | 2017-02-05 | 1999-08-09 | 2017-02-02 | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqProfessional | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqRestatementType | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqState | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | Capital IQ | CAPIQ_DBO.ciqSubType | 2017-02-05 | -- | -- | 2017-02-03 | Pass | Monthly
C+ | GBT
EDL | SSC_EDL_SOAR | SSC_EDL_SOAR.ORDERS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SOAR | SSC_EDL_SOAR.PRIORD | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SOAR | SSC_EDL_SOAR.TOPORDER | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.ANALYZER_V | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.MATERIAL | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.MATERIAL_AGG_DLY | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.MATERIAL_CSEG | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.MATERIAL_SLOC | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.MATERIAL_V | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.MRP_DATA | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.PO_DELIVERY_SCHED | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.PURCHASE_ORDER | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.STOCK_VALUATION | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.STOCK_VALUATION_HS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SAP_ODS | SSC_EDL_SAP_ODS.SUB_CONTRACT_STK | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | PEPIN | SSC_EDL_PEPIN.BUILDCAP | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | PEPIN | SSC_EDL_PEPIN.ETTC | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | PEPIN | SSC_EDL_PEPIN.SOPDEMAND | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | PEPIN | SSC_EDL_PEPIN.SUPPLYCMT | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | PEPIN | SSC_EDL_PEPIN.TECHTRAN | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | OIM_SALES | SSC_EDL_OIM_SALES.HW_AM_FEATURES_O | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2PCOMN | SSC_EDL_MFS2PCOMN.FCSPDDAD10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010P | SSC_EDL_MFS2P010P.FCSPOR10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010P | SSC_EDL_MFS2P010P.FCSPTL10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010N | FCSPOR10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010N | FCSPTL10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010 | FCSPOR10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010 | FCSPTL10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010A | FCSPOR10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010A | FCSPTL10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010C | FCSPOR10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010L | FCSPOR10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MFS2P010L | FCSPTL10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICSAMF | SSC_EDL_MAPICSAMF.DEMAND | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICSAMF | SSC_EDL_MAPICSAMF.DEMAND_T | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICSAMF | SSC_EDL_MAPICSAMF.MATERIALUNITCOST | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICSAMF | SSC_EDL_MAPICSAMF.MATERIALUNITCOST_T | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICSAMF | SSC_EDL_MAPICSAMF.OPENINV | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICSAMF | SSC_EDL_MAPICSAMF.ORDERS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.BUYERF | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.FIINVSS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.FIORDER | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.ITEMASA | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.ITEMASC | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.MLFPIPRFL | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.MLFPSB60 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.MLMMOADB | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.MTTOBRAND | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.POITEM | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.REQMTS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | MAPICS | SSC_EDL_MAPICS.VENNAM | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | LDW | SSC_EDL_LDW.IDM_WW_I01_ALL | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | LDW | SSC_EDL_LDW.IDM_WW_I01_AP | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | LDW | SSC_EDL_LDW.IDM_WW_I02_ALL | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | LDW | SSC_EDL_LDW.IDM_WW_I02_AP | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | LDW | SSC_EDL_LDW.PARETOREVENUEYEAR | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | LDW | SSC_EDL_LDW.RAWODS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ISICWINTEG | SSC_EDL_ISICWINTEG.LI_COMMIT | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ISICWINTEG | SSC_EDL_ISICWINTEG.LI_CROSS_REF | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ISICWINTEG | SSC_EDL_ISICWINTEG.LI_FORECAST | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ISICWINTEG | SSC_EDL_ISICWINTEG.LI_INVENTORY | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ISICWINTEG | SSC_EDL_ISICWINTEG.LI_INVENTORY_DLY | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ISICWINTEG | SSC_EDL_ISICWINTEG.LI_MM | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ISICWINTEG | SSC_EDL_ISICWINTEG.LI_MM_H | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ISICWINTEG | SSC_EDL_ISICWINTEG.LI_ORDER_BOOK | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ISICWINTEG | SSC_EDL_ISICWINTEG.LI_REPLENISHMENT | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ISICWINTEG | SSC_EDL_ISICWINTEG.LI_REPLENISHMENT_DLY | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | INZA | SSC_EDL_INZA.GEOMETRY_COLUMNS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | INZA | SSC_EDL_INZA.NZA_META_COLPROPS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | INZA | SSC_EDL_INZA.NZA_META_COMPONENTS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | INZA | SSC_EDL_INZA.NZA_META_MODELS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | INZA | SSC_EDL_INZA.NZA_META_PARAMS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | INZA | SSC_EDL_INZA.NZ_MAT_BRDCST_COMMAND | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | INZA | SSC_EDL_INZA.NZ_MAT_METADATA | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | INZA | SSC_EDL_INZA.SPATIAL_REF_SYS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | FNP | SSC_EDL_FNP.WW_ORD_CUR | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | FNP | SSC_EDL_FNP.WW_ORD_PR | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | FLE1P010 | SSC_EDL_FLE1P0101.FLEPPH10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | FLE1P010 | SSC_EDL_FLE1P0101.FLEPSH10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | FLE1P010 | SSC_EDL_FLE1P0101.FLEPSL10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | COVINFOS | IBM_PLANT_ORDER | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | COVINFOS | PROD_REF | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DB2COATG | SSC_EDL_DB2COATG.COA9A0T0 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DB2COATG | SSC_EDL_DB2COATG.COJ1J0T0 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DB2COATG | SSC_EDL_DB2COATG.COJ4J0T0 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DB2COATG | SSC_EDL_DB2COATG.COS1S0T0 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DB2COATG | SSC_EDL_DB2COATG.COS8S0T0 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DB2COATG | SSC_EDL_DB2COATG.COS8S0T0_T | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DCS1P010 | LOFPIX10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DCS1P010 | LOFPJT10 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DSNP | IBM_PLANT_ORDER | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DSNP | SAR | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DSNP | WW_ORD_CUR | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | DSNP | WW_ORD_PR | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ENOVIA | BASE_RELATIONS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ENOVIA | DEMAND_PN_ANALYSIS_LIST | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ENOVIA | ESZ_DECLARE_PARTS_EXP | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ENOVIA | ESZ_DECLARE_PARTS_EXP_2 | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | ENOVIA | PN_TEST | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | FFXT1 | V_APPLIANCE_ORDERS | 2017-01-12 | -- | 2017-01-12 | 2017-01-12 | Pass | Daily |  |  |  |  | ETL refresh jobs not scheduled yet
EDL | SCIWSTG | ISW_BUS_PARTNERS_V | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BPDM | JDBC1_BPAM_RF_BPDB_PARTNERS | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BPDM | TEST2_BPAM_RF_BPDB_PARTNERS | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BPDM | WSDIW_BPAM_RF_BPDB_PARTNERS | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BPDM | WSDIW_BPAM_SO_T1T2 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BPDM | WSDIW_BPAM_SO_T1T2_T | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.BPAM_RF_BPDB_PARTNERS_BU4 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.BPAM_SO_T1T2_BU1 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.BUS_PARTNERS_BU1 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.CISF_CLIENT_DATA_BU1 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.CMR_V_BU2 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.CUST_SAP_DIM_COVERAGE_BU1 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.ISW_OPPORTUNITIES_V_BU1 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.ISW_OPPORTUNITIES_V_BU2 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.ISW_OPPORTUNITIES_V_BU3 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.OPPORTUNITIES_BUS_PARTNERS_BU2 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.OPPORTUNITIES_V_BU2 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
EDL | BACCADM | CLD_EDL_BACCADM.WSDIW_BPAM_SO_T1T2_BU6 | 2017-01-12 |  | 2017-01-12 | 2017-01-12 | Pass | NONE
CI PDA | CIDM | BG_GLOBAL_BUYING_GROUP | 2016-12-07 |  |  |  | Pass
CI PDA | CIDM | CUST_SAP_COVERAGE_CUSTOMER | 2016-12-07 |  |  |  | Pass
CI PDA | CIDM | REF_GEO | 2016-12-07 |  |  |  | Pass
CI PDA | CIDM | REF_REGION | 2016-12-07 |  |  |  | Pass
CI PDA | CIDM | REF_COUNTRY_REGION | 2016-12-07 |  |  |  | Pass
CI PDA | CIDM | REF_CNTRY_SYSCD_ISOCD | 2016-12-07 |  |  |  | Pass
CI PDA | CIDM | LC_LEGAL_GBL_CLIENT | 2016-12-07 |  |  |  | Pass
CI PDA | FINANCE | CUSTOMER_SUB_BRAND_FACTS_V | 2016-12-07 |  |  |  | Fail - Schema not found
CI PDA | ISMCORE | SUB_BRAND_V | 2016-12-07 |  |  |  | Fail - Schema not found
CI PDA | WINLOSS | REV_CLIENT_WIN_LOSS | 2016-12-07 |  |  |  | Pass
CI PDA | WINLOSS | REV_CLIENT_WIN_LOSS_IOT | 2016-12-07 |  |  |  | Pass
CI PDA | WINLOSS | REV_CLIENT_WIN_LOSS_BRAND | 2016-12-07 |  |  |  | Pass
CI PDA | WINLOSS | REV_CLIENT_WIN_LOSS_SUB_BRAND | 2016-12-07 |  |  |  | Pass
CI PDA | Softlayer | adhoctemp.softlayer | 2016-12-07 |  |  |  | Fail - Schema not found
CI PDA | CIDM | LC_LEGAL_GBL_CLIENT | 2016-12-07 |  |  |  | Pass
CI PDA | CIDM | REF_CNTRY_SYSCD_ISOCD | 2016-12-07 |  |  |  | Pass
CI PDA | CIDM | REF_COUNTRY_REGION | 2016-12-07 |  |  |  | Pass
CI PDA | CIDM | REF_REGION | 2016-12-07 |  |  |  | Pass
Open Data | https://plants.usda.gov/java/downloadData?fileName=plantlst.txt&static=true | OPENDATA.PLANTS | 2017-02-09